# Project Proposal: DataExodus

Where Does My Data Go? Measuring Third-Party Data Flows on Australian Websites

# Background

Australians are told their data is handled responsibly, but nobody has measured what actually leaves the browser. Large tracking-measurement studies exist for the US and Europe, but none exist for Australian websites; Australian Privacy Principle (APP) 8, which governs sending personal information overseas, is untested in practice because these data flows are invisible to users; and privacy policies make vague claims about "selected partners" that nobody verifies against real traffic. This project builds a measurement tool and uses it to close that gap.

# Objectives

Build and verify a working data-flow measurement tool (browser extension, automated crawler, classification pipeline, and live dashboard) by Week 8.

Measure third-party data flows across 50 Australian websites (10 sites in each of 5 sectors) and test four hypotheses covering tracking prevalence, offshore data transfer, and privacy-policy accuracy by Week 11.

Produce a final report with a methodology reproducible by a third party, verified against DuckDuckGo Tracker Radar and manual review, submitted Week 12.

# Scope

The end result is a working tool (browser extension + crawler + classification pipeline + dashboard) and a study report covering 50 Australian websites. Work is delivered in three phases: foundation and prototype (Weeks 1–3), core build and literature review (Weeks 4–8), and full-scale measurement, analysis, and final reporting (Weeks 9–12). Explicitly out of scope: security testing, scanning, or exploitation of any target; collection of any traffic other than the student's own; and public deployment of the tool.

# Timeframe

| Description of Work | Start and End Dates |
| --- | --- |
| Phase One — Foundation & Charter: environment setup, extension and crawler prototype, charter submitted (A1) | Weeks 1–3 |
| Phase Two — Core Build & Literature Review: classification pipeline, personal-data detection, full 50-site crawl, dashboard, literature review (A2) and practical project plan (A3) | Weeks 4–8 |
| Phase Three — Analysis, Testing & Final Report: manual verification, hypothesis testing, privacy-policy comparison, final report and demonstration (A4) | Weeks 9–12 |

# Project Budget

| Description of Work | Anticipated Costs |
| --- | --- |
| Phase One — Foundation & Charter | $0.00 |
| Phase Two — Core Build & Literature Review | $0.00 |
| Phase Three — Analysis, Testing & Final Report | $0.00 |
| Total | $0.00 |

All hardware is student-owned (personal laptop; Raspberry Pi 5 for an optional phase) and all software is free/open-source (Python, Playwright, DuckDB, FastAPI, InfluxDB OSS, Grafana OSS), so the project carries no budget dependency.

# Key Stakeholders

Client: [Unit Teacher Name], TAFE NSW

Sponsor: [Unit Teacher Name], TAFE NSW

Project manager: Thanh Dat Phan

# Monitoring and Evaluation

Progress is evaluated against the four assessment events and a set of concrete quality measures:

| Measure | How it is checked |
| --- | --- |
| Classification accuracy | Compared against DuckDuckGo Tracker Radar |
| Personal data detection | Tested with deliberately planted known identifiers |
| Reproducibility | All 50 sites re-crawled after one week to check stability |
| Code quality | Automated tests, documented setup instructions |

The four hypotheses (over 60% of sites send data overseas; government/health sites carry fewer trackers than news/retail; over 30% of policies fail to name all observed third parties; hashed identifiers are transmitted by a measurable share of sign-up-form sites) are the final indicators of project success, tested and reported in Week 10.

# Approval Signatures

[Name], Project Client

[Name], Project Sponsor

Thanh Dat Phan, Project Manager

TAFE NSW

[Date]

This Project Proposal follows the structure of the Project Proposal Template by www.casual.pm.